## Stage Plan
Stage # | Track | Stage Name | Goal | Key Tasks | Depends On | Status | Notes
PHASE A — Backend Foundation (build and prove this before any UI exists)
A1 | Backend | Local dev environment | Get Supabase running locally via Docker so dev matches production from day one. | Install Docker · docker-compose.yml for local Supabase (Postgres, Auth, Storage) · confirm Supabase Studio loads locally · create GitHub repo | None | Not Started | This is the very first thing you touch — no Next.js yet.
A2 | Backend | Core schema design | Design and create the minimal tables the whole platform depends on. | profile table · projects table · skills table (optional, keep minimal) · media table · write schema as SQL migration files, not clicked in manually | A1 | Not Started | Keep it small. Add creative_blocks and resume_sections later, not now.
A3 | Backend | Row Level Security | Lock down the database before any frontend can touch it. | Enable RLS on every table · public policy = SELECT only on published rows · confirm anon key cannot INSERT/UPDATE/DELETE via Studio's SQL test | A2 | Not Started | Do this before you ever write frontend fetch code, so you build against real constraints.
A4 | Backend | Auth setup | Set up the one admin account that will manage content later. | Enable Supabase Auth (email/password is enough) · create your own admin user · write an admin-only RLS policy checked against auth.uid() | A3 | Not Started | You don't need the admin UI yet — just prove the policy works via Studio.
A5 | Backend | Seed data | Put real (or realistic placeholder) content into the database so the frontend has something true to render. | Add 2-3 real projects · write real bio content · upload a couple of real images to Storage · confirm they load via a public Storage URL | A2, A3 | Not Started | Use real content where you can — placeholder lorem ipsum makes later frontend decisions harder, not easier.
A6 | Backend | Data access layer | Write the shared functions every frontend experience will call — before any frontend exists. | lib/supabase client + server setup · typed fetch functions (getProfile, getProjects, getMedia) · generate TypeScript types from the Supabase schema | A5 | Not Started | This is the seam between backend and frontend — get it right once, both experiences reuse it.
PHASE B — Frontend Foundation (scaffold + prove the data connects)
B1 | Frontend | Next.js scaffold | Stand up the app shell and routing skeleton — no visual design yet. | Create Next.js + TypeScript + Tailwind project · set up app/ folder structure (developer, creative, story, admin placeholders) · connect env vars to local Supabase | A6 | Not Started | Every route can just say its own name on a blank page at this point.
B2 | Frontend | Prove the data connection | Confirm the frontend can actually read what Backend Phase A produced. | Call getProjects() on a plain page · render seeded project titles as plain text · confirm RLS blocks writes from the client | B1 | Not Started | This is a checkpoint, not a feature — once real data renders anywhere, Phase A is proven end-to-end.
B3 | Frontend | Boot loader + Entry page | Build the first thing a visitor actually sees. | Boot/loading animation · Entry/Choice page UI · links to /developer, /creative, /story (story can 404 gracefully for now) | B2 | Not Started | Keep the animation simple at first — polish later, once the rest works.
PHASE C — Developer Experience
C1 | Frontend | Developer layout + theme | Establish Developer's visual identity before filling it with content. | Developer-specific layout.tsx · dark/light CSS token pair for Developer · next-themes wired up · custom cursor component (Developer config) | B3 | Not Started | Prove theming + cursor on one experience before copying the pattern to Creative.
C2 | Frontend | Developer sections | Build the real scroll-based content, reading from the data access layer. | Hero · projects (rendered as technical cards from real project data) · skills · case studies · smooth scroll + micro-interactions | C1 | Not Started | Structure is code-controlled, not admin-editable — by design.
C3 | Frontend | Adaptive interactive resume | Build the resume as a mode inside Developer. | /developer/resume route · resume_sections table (back in Backend if needed) · simple visibility toggle logic (e.g. recruiter view vs full view) | C2 | Not Started | Start with static toggled sections — don't build a rules engine yet.
PHASE D — Creative Experience
D1 | Backend | Creative schema | Add the spatial data model the canvas needs. | creative_blocks table (type, content_ref, x, y, width, height, rotation, z_index, visibility) · RLS: public SELECT, admin CRUD | A6 | Not Started | Do this small backend addition right before you need it, not back in Phase A.
D2 | Frontend | Canvas engine | Build the pan/zoom/drag mechanics with placeholder blocks. | Base canvas component · pan/zoom/drag interactions · render placeholder rectangles at fixed positions first | B3 | Not Started | Prove the interaction model before it needs to read real data.
D3 | Frontend | Creative theme + cursor + real blocks | Connect the canvas to real data and give Creative its own identity. | Creative dark/light tokens · custom cursor Creative config (magnetic hover) · fetch real creative_blocks and render as positioned objects · block type renderers (text/image/project/gallery) | D1, D2 | Not Started | This is where Creative starts to feel like its own world, distinct from Developer.
PHASE E — Admin
E1 | Backend | Admin auth gate | Lock the /admin route behind real authentication. | Supabase Auth session check in middleware · redirect unauthenticated visitors · confirm hidden route is not the actual security boundary | A4, B1 | Not Started | Content editing itself (bio/projects/images) happens directly in Supabase Studio — no custom UI needed for that.
E2 | Frontend | Creative canvas editor | Build the one custom admin surface that's actually needed — the Figma-style editor. | Layers panel · properties panel (x, y, width, height, rotation, visibility) · add/delete/duplicate block · drag-to-move, drag-to-resize · save to creative_blocks | D3, E1 | Not Started | This is the only piece Supabase Studio can't give you — spatial data isn't meaningfully editable in a table.
E3 | Frontend | Preview / publish (optional) | Decide if draft vs published state is worth it for a personal site. | Add draft boolean to creative_blocks if useful · preview toggle in editor · publish action | E2 | Not Started | Skip this stage entirely if direct-save is good enough for your use case.
PHASE F — Story, Mobile & Deployment (later, once the core product works)
F1 | Both | Story experience | Build the third experience, now that the pattern is proven twice already. | Three.js / React Three Fiber scene · scroll-driven camera movement · narrative content structure (write this out separately when you reach it) | C2, D3 | Not Started | Deliberately last among the three experiences — highest risk, most novel tech.
F2 | Frontend | Mobile experiences | Give Developer and Creative dedicated mobile renderers. | Mobile Developer layout (not a shrink of desktop) · touch-first Creative canvas (pinch-zoom, tap, double-tap focus) · disable custom cursor on touch | C2, D3 | Not Started | Same backend, same data access layer — only the rendering logic is new.
F3 | Both | Deployment polish | Finalize the path from local Docker dev to production. | Vercel project + env vars pointing at hosted Supabase · confirm RLS policies match production expectations · final Docker Compose docs for future local setup | A1-A6, all frontend stages | Not Started | Docker stays a local dev tool throughout — Vercel builds from source, not from the Docker image.